# Day-of-Show Run Sheet / Show Flow

The stage manager’s (or TM’s) minute-by-minute plan for the day. Build one per show from the advance, distribute to crew and venue the morning of, and run the day off it. Times are local. Keep one printed copy at the production desk and one at stage.

## Show Info (Header)

- Date: [FILL IN] Day: [FILL IN]

- Venue: [FILL IN] City: [FILL IN]

- Capacity: [FILL IN] Doors: [FILL IN] Curfew: [FILL IN]

- Headliner: [FILL IN] Support: [FILL IN]

- Stage Manager: [FILL IN] ([phone])

- Tour Manager: [FILL IN] ([phone])

- Venue Production Contact: [FILL IN] ([phone])

- Show type: [Live band / DJ set / Hybrid]

- Set length: Headliner [FILL IN] min · Support [FILL IN] min

## Run of Day

Fill the Time column with real local times during the advance. Keep rows in order; adjust the template to match your call times.

| Time | Cue / Activity | Who | Notes |
| --- | --- | --- | --- |
| [10:00] | Crew call / venue access | TM, venue prod | Confirm power, access, parking for [VEHICLE] |
| [10:00] | Load-in begins | All crew, venue stagehands | [# of stagehands advanced], loading dock at [location] |
| [10:30] | Backline / gear stage placement | Backline tech, band | Mark stage with spike tape |
| [11:00] | Audio system check (PA, FOH, monitors) | FOH eng, venue audio | Verify input list / patch matches advance |
| [11:30] | Lighting focus & program | LD, venue LX | Load show file; note any house-light cues |
| [12:00] | Video / visuals load + test (if applicable) | VJ / video tech | Confirm resolution, feed to LED/screens |
| [12:30] | Line check (channel by channel) | FOH, monitors |  |
| [13:00] | Lunch (crew) | All | [Catering / buyout] — see hospitality rider |
| [14:00] | Headliner soundcheck | Artist, FOH, monitors | [Duration]; build monitor mixes, set virtual check if DJ |
| [15:00] | Support soundcheck / line check | Support act, FOH | Keep to [X] min |
| [15:30] | Stage reset to top-of-show positions | Stage crew | Re-spike, tape down cables, set risers |
| [16:00] | Merch load-in & setup | Merch seller, venue | Confirm % to house, count-in sheet started |
| [16:30] | Settle hospitality / green room | TM, venue | Confirm rider, towels, water, meal times |
| [17:00] | Guest list to box office | TM | Final GL count: [#]; will-call instructions |
| [17:30] | Production meeting / safety walk | SM, all dept heads | Review changeover, encore, emergency exits |
| [18:00] | Crew dinner | All |  |
| [18:45] | Final stage check, clear stage | SM | Cables taped, fire lanes clear, fresh towels/water |
| [19:00] | DOORS | Venue front of house | SM confirm with venue mgr before opening |
| [19:30] | Walk-in music / house playlist | Venue / VJ | [Playlist source] |
| [20:00] | Support set START | Support act | SM call: “5 to stage” at 19:55 |
| [20:35] | Support set END | Support act | Hard out by [time] |
| [20:35] | CHANGEOVER ([X] min) | Stage crew, techs | Reset backline, line check, refresh DJ booth, swap risers |
| [21:00] | Headliner set START | Artist | SM call: “Artists to stage” at 20:55; intro/walk-up cue |
| [22:20] | Last song before encore break | Artist, SM | SM cues lighting/blackout |
| [22:20] | Encore break | Artist, SM | [If applicable] hold [1–2] min, audience hold |
| [22:23] | Encore | Artist | [# of songs] |
| [22:30] | Headliner set END / house lights up | SM, venue LX | Curfew: [time] — must end by |
| [22:30] | Walk-out music | Venue / VJ |  |
| [22:35] | Merch settle & pack | Merch seller, TM | Final count-out, reconcile vs. start count |
| [22:45] | Load-out begins | All crew, stagehands | Strike stage, coil cables, case backline |
| [23:00] | Settlement | TM, promoter | Reconcile tickets, expenses, merch %, pay-out |
| [23:45] | Final venue sweep / lost-and-found check | TM, SM | Green room, stage, FOH cleared |
| [00:00] | Load-out complete / depart | All | Next: [hotel / drive / next city] |

## Set Timing Quick Reference

| Slot | Start | End | Length | Curfew buffer |
| --- | --- | --- | --- | --- |
| Support | [FILL IN] | [FILL IN] | [FILL IN] | — |
| Changeover | [FILL IN] | [FILL IN] | [FILL IN] | — |
| Headliner | [FILL IN] | [FILL IN] | [FILL IN] | [min before curfew] |
| Encore | [FILL IN] | [FILL IN] | [FILL IN] | — |

## Notes & Contingencies

- Curfew is hard. Confirm the overage penalty with the promoter and build the encore so the show ends [X] minutes before curfew.

- Changeover discipline: the changeover is the most common cause of a late show. Pre-stage everything possible during the support set.

- DJ / electronic show variant: replace band soundcheck with a USB/booth check (CDJs/mixer, headphone monitor, booth-monitor level) and a 5-minute “virtual check.” Changeovers are faster — confirm B2B or back-to-back DJ transitions and who controls the mixer hand-off.

- Weather / outdoor: add a lightning/weather hold protocol and decision-maker.

- Emergency: nearest hospital [FILL IN]; venue evac plan reviewed at production meeting; SM holds the master cue to stop the show.

Distribute to: TM, SM, FOH, monitors, LD, backline, merch, venue production, support act TM. Update the printed copy if times shift during the day.