## Timeline
Release Campaign Timeline
Weeks Out | Phase | Task | Owner | Done?
8 | Setup | Finalize master, artwork, metadata; get ISRC/UPC
8 | Setup | Deliver to distributor
6 | Pitch | Submit to Spotify/Apple editorial (4+ wks before)
6 | Pitch | Send to playlist curators & press
4 | Tease | Begin content teasers / pre-save link live
3 | Tease | Behind-the-scenes / snippet drops
2 | Push | Press premiere / interviews
1 | Push | Final countdown content, paid ads live
0 | Release | Release day: post everywhere, thank curators, story stack
+1 | Sustain | Push reactions/UGC, pitch next playlists
+2 | Sustain | Recap metrics, plan follow-up single/visual